## Test Plan
Please click here for Lazz Pharma Limited testplan full PDF.

## Mind Maps
Mind Map of Lazz Pharma Limited

## TestScenarios
Project Name | Lazz Pharma Limited
Reference Document | FRS
Created By | Md. Kawsar Hossain
Creation Date | 18/04/2025
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 | Account | Validate login, signup, and password reset and logout functionality with proper redirection. | P0 | 37
TS_002 |  | Validate logged-in user features like profile editing, order history, prescription uploads. | P1 | 36
TS_003 | Home | Validate homepage banners, marquees, featured sections, and redirections. | P0 | 27
TS_004 | Product Management | Validate navigation and product listing in all 15 categories. | P0 | 9
TS_005 |  | Validate product search functionality with accurate and relevant results. | P0 | 12
TS_006 |  | Validate product card and product details page components (name, price, review, add to bag, etc). | P0 | 9
TS_007 |  | Validate adding, updating, and removing items from the cart and placing an order. | P0 | 8
TS_008 |  | Validating checkout functionalities | P0 | 24
TS_009 | Request Order | Validate request order form inputs, validations, prescription upload, and receiver info. | P1 | 17
TS_010 | Special Offer | Validate special offer listings, visibility, and link redirections. | P2 | 5
TS_011 | Branch Locations | Validate search functionality, branch details, and map integration. | P1 | 9
TS_012 | Company Info | Validate reviews, gallery, about us, contact us and Franchise info page content and functionality | P2 | 28
TS_013 | Footer | Validate footer links, social icons, contact info, and policy pages. | P1 | 18
TS_014 | General | Validate website compatibility across browsers and device sizes (responsive test). | P0 | 2

## TestCase
Product Name |  | Lazz Pharma Limited | TC Start Date | 19/04/2025 | TC Execution Start Date | - - | [5 empty] | TEST CASE
Module Name |  |  | TC End Date |  | TC Execution End Date | - - |  |  |  |  | PASS | 227
Epic |  |  | Test Case Developed By | Md. Kawsar Hossain | Browser (tested) | Yes |  |  |  |  | FAIL | 11
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 3
[11 empty] | TOTAL | 241
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account |  | Sign Up | Verifying phone number, password and confirm password fields are displayed on the signup modal | Phone Number, Password and Confirm Password field should be displayed on the Signup Modal | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Sign Up |  |  | Passed
2 |  |  |  | Verifying users are notified if the phone number is invalid in Signup modal | Invalid phone number should be detected | Not found as per expected. After entering invalid phone number users are taken to the OTP input modal | 173206680 | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Sign Up Step-4: Type an invalid Phone number Step-5: Type Password and Confirm Password and enter | Invalid_phone_number_error.png |  | Failed
3 |  |  |  | Verifying all the fields are required to signup | Phone Number, Password and Confirm Password should be mandatory to signup | Found as per expected | 01732066805, liliput, liliput | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Sign Up Step-4: Submit without some fields |  |  | Passed
4 |  |  |  | Verifying OTP is generating after signup attempt and is sent to user's phone | User should receive OTP on their given phone number | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Sign Up Step-4: Fill all the field and signup |  |  | Passed
5 |  |  |  | Verifying invalid OTP is caught and user is notified about the wrong OTP | User should be notified if they input wrong OTP | Found as per expected with error message showing "Wrong OTP." | 3245 | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Sign Up Step-4: Fill all the field and signup Step-5: Enter a wrong OTP |  |  | Passed
6 |  |  |  | Verifying user can signup with actual OTP | User should be able to signup with the actual OTP | Found as per expected | 5522 | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Sign Up Step-4: Fill all the field and signup Step-5: Enter the actual OTP |  |  | Passed
7 |  |  |  | Verifying user can resend OTP to their phone | User should be able to resend OTP to their Phone Number | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Sign Up Step-4: Click on resend |  |  | Passed
8 |  |  |  | Verifying Password and Confirm Password fields requires the same password | User should input same password in both Password and Confirm Password Field, If not the user should be notified | Found as per expected with error message "Password did not match" | liliput,lalaput | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Sign Up Step-4: Fill all the field and Input Different password in Password and Confirm Password Step-5: Click on SignUp |  |  | Passed
9 |  |  |  | Verifying existing customer is notified if they try to signup | Already Registed users should be notified if they try to Signup | Found as per expected with error message "This Customer is already exist." |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Sign Up Step-4: Fill all the field Step-5: Click on SignUp |  |  | Passed
10 |  |  |  | Verifying users are redirected to specified page after successfull signup | Users should be redirected to a specified page after successfull signup | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Sign Up Step-4: Fill all the field Step-5: Click on SignUp |  |  | Passed
11 |  |  |  | Verifying Login button disappears after successful signup | Login button should not appear after successful signup | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Sign Up Step-4: Fill all the field Step-5: Click on SignUp |  |  | Passed
12 |  |  | Login | Verifying login modal appears after clicking on login button | Login modal should appear after clicking on Login Button | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login |  |  | Passed
13 |  |  |  | Verifying both the phone and password field is required to Login | Users shouldn't be allowed to Login without providing registered phone and password both | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login |  |  | Passed
14 |  |  |  | Verifying user is notified if Phone or Password field is empty | User should be notified if Phone Number/ Password field is empty | Found as per expected with error message showing "Password number is empty" | 1732066805 | Step-1: Go to Site Step-2: Click on Login Step-3: Enter Phone/Password Only Step-4: Click on Login |  |  | Passed
15 |  |  |  | Verifying user is notified if the user try to login with unregistered Phone number | User should be notified if Phone Number is not registered | Found as per expected with error message showing "You are not Registered." | 1732066802 | Step-1: Go to Site Step-2: Click on Login Step-3: Enter Phone and Password Step-4: Click on Login |  |  | Passed
16 |  |  |  | Verifying user is notified if they enter wrong password | User should be notified if the password doesn't match | Found as per expected with error message showing "Phone number or password does not match." | 01732066805,lalaput | Step-1: Go to Site Step-2: Click on Login Step-3: Enter Phone and Invalid Password Step-4: Click on Login |  |  | Passed
17 |  |  |  | Verifying users can login with valid login credentials | Users should be allowed to login with valid credentials | Found as per expected | 01732066805,liliput | Step-1: Go to Site Step-2: Click on Login Step-3: Enter Phone and Password Step-4: Click on Login |  |  | Passed
18 |  |  |  | Verifying users are redirected to specified page after successfull login | Users should be redirected to a specified page after successfull login | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Enter Phone and Password Step-4: Click on Login |  |  | Passed
19 |  |  |  | Verifying login button disappears after successful login | Login button should not appear after successful login | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Enter Phone and Password Step-4: Click on Login |  |  | Passed
20 |  |  |  | Verifying users are not logged out on closing the page or refreshing the page | Users shouldn't be logged out if they close the page or refresh the page in logged in state | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Enter Phone and Password Step-4: Click on Login Step-5:Close the tab/refresh the tab |  |  | Passed
21 |  |  |  | Verifying logged in user's protected URL isn't accessible by copying into other browser or from other account | The URL shouldn't be accessible and it should redirect to home page if tried to access | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Enter Phone and Password Step-4: Click on Login Step-5:Cope a private url to another browser |  |  | Passed
22 |  |  |  | Verifying user can access the reset password modal by clicking on reset password | Users should be able to view the reset password modal by clicking on reset password | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Reset Password |  |  | Passed
23 |  |  |  | Verifying all the fields are required to reset password | User should fill out Phone number, Password and Confirm Password Field to reset their password | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Reset Password |  |  | Passed
24 |  |  |  | Verifying both the password and confirm password mismatch is caught in the reset modal | If the Password and Confirm password doesn't match users should be notified with a message | Found as per expected with error message "Password did not match" | asas,asad | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Reset Password Step-4: Enter different password on Password and Confirm Password Field |  |  | Passed
25 |  |  |  | Verifying user can go back to the login modal by clicking on login from reset password modal | Users should be allowed to go back to login modal by clicking on login | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Reset Password Step-4: Click on Login |  |  | Passed
26 |  |  |  | Verifying OTP is sent to user's phone after successful reset request | User should receive OTP on their given phone number | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Reset Password Step-4: Fill out the fields and click on reset |  |  | Passed
27 |  |  |  | Verifying with valid OTP user can reset their password | User should be able to reset their password by entering valid OTP | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Reset Password Step-4: Fill out the fields and click on reset Step-5:Enter the OTP sent to the Phone |  |  | Passed
28 |  |  |  | Verifying invalid OTP is caught and user is notified about the wrong OTP during password reset | Invalid OTP should be caught and users should be notified | Found as per expected with error message "Wrong OTP" |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Reset Password Step-4: Fill out the fields and click on reset Step-5:Enter invalid OTP |  |  | Passed
29 |  |  |  | Verifying new OTP is sent to user after clicking on resend OTP | New OTP should be sent to the user | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Reset Password Step-4: Fill out the fields and click on reset Step-5:Click on Resend |  |  | Passed
30 |  |  |  | Verifying user can login with their new password after successfull password reset | User should be able to login with their new password after password reset | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Reset Password Step-4: Fill out the fields and click on reset Step-5:Enter valid OTP and reset Step-6: Login with the new password |  |  | Passed
31 |  |  |  | Verifying user can not login with their old password after successfull password reset | User should not be able to login with their old password after password reset | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Reset Password Step-4: Fill out the fields and click on reset Step-5:Enter valid OTP and reset Step-6: Login with the old password |  |  | Passed
32 |  |  |  | Verifying user is logged in automatically after successfull password reset | User should be logged in automatically after successfull password reset | Found as per expected |  | Step-1: Go to Site Step-2: Click on Login Step-3: Click on Reset Password Step-4: Fill out the fields and click on reset Step-5:Enter valid OTP and reset |  |  | Passed
33 |  |  | Logout | Verifying user can logout from the site by clicking on logout | User should be able to logout from the system by clicking on logout | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Click on Profile Step-4: Click on Logout |  |  | Passed
34 |  |  |  | Verifying user can go back to the last protected page by clicking on browser back button after successfull logout | User shouldn't be able to access any account related information once they logout from the site | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Click on Profile Step-4: Click on Logout Step-5:Click on Browser back button |  |  | Passed
35 |  |  |  | Verifying logout option isn't available while the user isn't logged in | User shouldn't see the logout option unless they are logged in | Found as per expected |  | Step-1: Go to Site |  |  | Passed
36 |  |  |  | Verifying users are logged out from all the tabs if multiple tabs are open and the user logs out from a single tab | User should be logged out from all the other tabs once the user logs himself out | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Duplicate multiple tabs Step-4:Logout from any single tab |  |  | Passed
37 |  |  |  | Verifying user is redirected to the home page once the user click on logout | User should be redirected to the homepage if they logout | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3:Logout |  |  | Passed
38 |  |  | Edit Profile | Verifying user can access the edit profile page once they login | USer should be able to edit profile | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Edit Profile |  |  | Passed
39 |  |  |  | Verifying user cannot edit their phone number from the edit profile page | The phone number field should be read only | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Edit Profile |  |  | Passed
40 |  |  |  | Verifying user can edit their name and email from edit profile | User should be able to change or edit their name or email | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Edit Profile Step-4: Edit name/email and save |  |  | Passed
41 |  |  |  | Verifying user can change their profile picture from the edit profile option | User should be able to change their profile picture | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Edit Profile Step-4: Choose Profile Picture |  |  | Passed
42 |  |  |  | Verifying changes made to the profile stays the same even after relogging into the site | User information should be stored and they should be able to see it unchanged if they login to the system later | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Edit Profile Step-4: Choose Profile Picture Step-5: Logout Step-6: Login again |  |  | Passed
43 |  |  | Order History | Verifying user can access the order history page | User should be able to access the user history page | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History |  |  | Passed
44 |  |  |  | Verifying user is shown a meaningful message if the user has no order history | User should be shown a meaningful message if no orders were made in the past | Found as per expected with message "No Order Found!" |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History |  |  | Passed
45 |  |  |  | Verifying if the user has order history all the past orders are shown in this page | All the past order made by this account should be displayed in this page | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History |  |  | Passed
46 |  |  |  | Verifying each order has its own Order ID | Each previous order should have their own order ID | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History |  |  | Passed
47 |  |  |  | Verifying order related information are displayed for each order | Each order should have Order Date, Status, Payable Amount and Delivery address on those | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History |  |  | Passed
48 |  |  |  | Verifying user can reoder any past order | User should be able to reorder using the refil button | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History Step-4: Click on Refil Step-5: Click on Order |  |  | Passed
49 |  |  |  | Verifying clicking on refil loads a modal | Clicking on refil button on any order should open up a modal consisting of the products of that order and the cost and other infos | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History Step-4: Click on Refil |  |  | Passed
50 |  |  |  | Verifying spelling mistake on refil modal | There shouldn't be any spelling mistake on the modal | Not found as per expected. The spelling of "Cancel" is wrongly displayed as "Cancle" |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History Step-4: Click on Refil | refil_modal_spelling_error.png |  | Failed
51 |  |  |  | Verifying clicking on view details buttons of any order takes the user to order details page | Clicking on view details buttons of any order should take the user to order details page | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History Step-4: Click on View Details |  |  | Passed
52 |  |  |  | Verifying order processing status is displayed on order details page | Order processing status should be displayed on order details page | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History Step-4: Click on View Details |  |  | Passed
53 |  |  |  | Verifying order related all kinds of information are displayed on order details page | Order related all kinds of information should be displayed on order details page | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History Step-4: Click on View Details |  |  | Passed
54 |  |  |  | Verifying user can print invoice | User should be able to print invoice by clicking on print invoice button | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Order History Step-4: Click on View Details |  |  | Passed
55 |  |  | Prescription History | Verifying user can access the prescription history page once they are logged in | Logged in user should have access to the prescription history page | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Prescription History |  |  | Passed
56 |  |  |  | Verifying the reasons for the prescription upload are clearly stated on the page | The reasons/benefit of prescription upload should be clearly stated on the prescriptioon history page | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Prescription History |  |  | Passed
57 |  |  |  | Verifying prescriptions can be uploaded on on the prescription history page | Should be able to upload prescription on the prescription history page | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Prescription History Step-4: Upload a prescription |  |  | Passed
58 |  |  |  | Verifying once the prescription is uploaded, order can be placed bases on that prescription | User should be able to order by uploading their prescription | Not found as per expected.after uploading prescription and adding note order can't be placed by clicking on the save and order button |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Prescription History Step-4: Upload a prescription and add note Step-5: Click on Save & Order |  |  | Failed
59 |  |  |  | Verifying previously uploaded prescription are found on the prescription history | User should be able to see their previously uploaded prescription | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Prescription History Step-4: Upload a prescription and refresh the page |  |  | Passed
60 |  |  |  | Verifying previous prescription can be downloaded, selected or can be removed | User should be able to download, select or remove prescription | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Prescription History Step-4: Upload a prescription and refresh the page |  |  | Passed
61 |  |  |  | Verifying Upload Prescription button on the navbar takes the user to the prescription history page | User should be redirected to the Prescription History page if they click on Upload Prescription | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Click on Upload Prescription |  |  | Passed
62 |  |  | Request History | Verifying user can access the request history page | User should be able to access the request history page if they are logged in | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Request History |  |  | Passed
63 |  |  |  | Verifying a message is displayed if not request is made | User should be shown a message about no request being made till now | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Request History |  |  | Passed
64 |  |  |  | Verifying request are shown in request history page once the request was made | User should be able to see all their request till now in request history | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Request History |  |  | Passed
65 |  |  |  | Verifying request information are also present along with the request | User should be able to see the detailed request information | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Request History |  |  | Passed
66 |  |  |  | Verifying request status is shown | User should be able to see a status of their request | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Request History |  |  | Passed
67 |  |  |  | Verifying clicking on view button of a request shows the requested product information | User should be able to see the product name,strength and quantity they requested by clicking on view button | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Request History Step-4: Click on View button of a request |  |  | Passed
68 |  |  | Submit Complain | Verifying logged in user can access submit complain page | User should be able to access submit complain page if they are logged in | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Submit Complain |  |  | Passed
69 |  |  |  | Verifying all the fields(Description, Complain Selection) is required to submit complain | User should fill out the complain description and Select Complain category to submit a complain | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Submit Complain Step-4: Try to submit with one/any field empty |  |  | Passed
70 |  |  |  | Verifying user can submit complain | User should be able to submit complain | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Submit Complain Step-4: Submit a complain |  |  | Passed
71 |  |  |  | Verifying a message is shown once the complain is submitted | User should see a success message once a complain has been filed | Found as per expected with success message "Submit Complain Successfully". |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Submit Complain Step-4: Submit a complain |  |  | Passed
72 |  |  | Payment History | Verifying user can access the payment history page | User should be able to access the payment history page | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Payment History |  |  | Passed
73 |  |  |  | Verifying user can see their past payment history in payment history page | User should be able to see their past payment history | Found as per expected |  | Step-1: Go to Site Step-2: Login to the site Step-3: Go to Payment History |  |  | Passed
74 | Home |  | Banner | Verifying a banner is showing on homepage | There should be a banner on homepage | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
75 |  |  |  | Verifying the banner has 5 image in the carousal | Five images should be there on the banner carousal | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
76 |  |  |  | Verifying next and previous button are working on all the images of the carousal | Smooth navigation should be done with the next and previous button | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Click on Next/Previous button of the carousal |  |  | Passed
77 |  |  |  | Verifying no grammartical or spelling mistake is there on the carousal | There should be no grammartical or spelling mistake | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Click on Next/Previous button of the carousal |  |  | Passed
78 |  |  | Marquee | Verifying the marquee is running | The marquee should run on | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
79 |  |  |  | Verifying the marquee stops on mouse hover | The marquee should pause on mouse hover | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3 : Hover on marquee |  |  | Passed
80 |  |  |  | Verifying the marquee showing specified information | The marquee should show contact info for medicine related information seeking and new franchise branch openning application related information seeking helpline | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
81 |  |  |  | Verifying the text on the marquee has no grammartical or spelling mistake | The text on marquee shouldn't have any grammartical or spelling mistake | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
82 |  |  | Service Highlights | Verifying service highlights are showing under the marquee | Four service highlights should be displayed under the marquee | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
83 |  |  |  | Verifying service highlights section has no grammartical or spelling mistakes | The service highlight section shouldn't have any grammartical or spelling mistake | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
84 |  |  |  | Verifying franchise related information highlight takes the user to a specified page | New franchise of Lazzpharma related highlight should take the user to a page where franchise related information are displayed | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Click on Franchise releted highlight |  |  | Passed
85 |  |  |  | Verifying authentic medicine highlight takes the user to prescription medicine page | Authentic Medicine Highlight should ttake the user to prescription medicine page | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Cick on Authentic Medicine Highlight |  |  | Passed
86 |  |  |  | Verifying Order Surgical Product highlight takes the user to surgical product page | Surgical Product Highlight should ttake the user to surgical product page | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Cick on Order Surgical Product Highlight |  |  | Passed
87 |  |  |  | Verifying upload prescription highlight takes the user to prescription history page | Upload prescription highlight should take the user to prescription history page | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Cick on Upload Prescription Highlight |  |  | Passed
88 |  |  | Featured Product | Verifying featured products contains products of several different categories | Featured products should contain products of several categories(Prescription Medicine, Surgical Product, OTC Medicine, Personal Care, Women's Care, Dental & Oral Care, Diabetic Care, Suppliments and Vitamins, Baby Care) | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
89 |  |  |  | Verifying each featured product category has the category name on top | Featured category name should be displayed on top of each featured section | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
90 |  |  |  | Verifying product Card on featured section has specific contents | Each Product card should have an Image, Product name, Generic Name/Type of product, Price and Add to Bag button | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
91 |  |  |  | Verifying clicking on any product on featured section redirects to the product details page | Clicking on any product should take the user to the details page of that particular product | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Click on a product of Featured Section |  |  | Passed
92 |  |  |  | Verifying the add to bag button on product card is working | Clicking on add to bag button on any product should add the product to cart | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Click add to bag button of several products on featured section |  |  | Passed
93 |  |  |  | Verifying quantity of product can be selected after clicking on add to bag button | After clicking on add to bag button user can increase or decrese quantity to select their choice of quantity for that particular product | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Click add to bag button Step-4: Click on +/- button to increase/decrease quantity |  |  | Passed
94 |  |  |  | Verifying whether the product is selected if the quantity is less than 1 | If the quantity becomes less than 1 then the add to bag button should be back and the product would be removed from the cart | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Click add to bag button Step-4: Click on - button to decrease quantity to less than 1 |  |  | Passed
95 |  |  |  | Verifying next/previous navigation button for the featured categories are working | The next/previous button of the featured categories should be able to navigate throughout the product | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Click on the navigation buttons of the featured sections |  |  | Passed
96 |  |  |  | Verifying Clicking on view all button of each featured categories takes the user to a page containing all the products of that category | Clicking on view all button of each featured categories should take the user to a page containing all the products of that category | Not found as per expected as clicking on view all doesn't take the user to all product list of that category |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Click on View all button of each category | view_all_button_error.mp4 |  | Failed
97 |  |  | Resort Banner | Verifying Lazz Polli Resort Image carousal banner is displayed at the bottom of home page | Lazz Polli Resort Image carousal banner should be displayed at the bottom of home page | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
98 |  |  |  | Verifying the carousal contains several image of the resort | The carousal should contain several images of the resort | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page |  |  | Passed
99 |  |  |  | Verifying banner navigation can be done with the next/previous navigation button | The carousal can be navigated by using the next/previous button | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Navigate the Resort Banner Carousal |  |  | Passed
100 |  |  |  | Verifying clicking on the banner takes the user to FB page of Lazz Polli Resort | Clicking on the banner should take the user to FB page of Lazz Polli Resort | Found as per expected |  | Step-1: Go to Site Step-2:Go to Home Page Step-3: Click on the resort banner |  |  | Passed
101 | Product Management |  | Categories | Verifying hovering on categories opens a dropdown containing all the product categories | Hovering on categories should open a dropdown containing all the categories | Found as per expected |  | Step-1: Go to Site Step-2:Hover on categories |  |  | Passed
102 |  |  |  | Verifying all the product categories are shown under category dropdown | All product categories should be displayed under categories dropdown | Found as per expected |  | Step-1: Go to Site Step-2:Hover on categories |  |  | Passed
103 |  |  |  | Verifying clicking on each product category takes the user to product list of that category | Clicking on each product category takes the user to product list of that category | Found as per expected |  | Step-1: Go to Site Step-2:Hover on categories Step-3: Click on a Category |  |  | Passed
104 |  |  |  | Verifying breadcrumbs on each product category page is showing the correct path | Breadcrumbs on each product category page should be showing the correct path | Found as per expected |  | Step-1: Go to Site Step-2:Hover on categories Step-3: Click on a Category |  |  | Passed
105 |  |  |  | Verifying products of certain category are displaying under that category | Product of specific category should be displayed under that category | Found as per expected |  | Step-1: Go to Site Step-2:Hover on categories Step-3: Click on a Category |  |  | Passed
106 |  |  |  | Verifying pages link shown under the product list can be visited | CLicking on any page number should take the user to that particular page | Found as per expected |  | Step-1: Go to Site Step-2:Hover on categories Step-3: Click on a Category Step-4: Click on Page number(eg. 1,2 etc) |  |  | Passed
107 |  |  |  | Verifying next/previous buttons in the pagination is working | Next/previous button in the pagination should take the user to the next/previous page of the current page | Found as per expected |  | Step-1: Go to Site Step-2:Hover on categories Step-3: Click on a Category Step-4: Click on Next/Previous button of the pagination |  |  | Passed
108 |  |  |  | Verifying clicking on a category displays a loader untill the category products are loaded | Clicking on any category should display a loader untill products are displayed | Found as per expected |  | Step-1: Go to Site Step-2:Hover on categories Step-3: Click on a Category |  |  | Passed
109 |  |  |  | Verifying if any category doesn't contain any product, user is shown a message | User should be displayed a message if no products are found under certain category | Not found as per expected, there is no message displayed in case of no product available |  | Step-1: Go to Site Step-2:Hover on categories Step-3: Click on Health Condition Category | product_unavailable_message_error.png |  | Failed
110 |  |  | Product Search | Verifying user can see the searchbar in all the pages on top of the page | User should be able to see the searchbar in all the pages of the site | Found as per expected |  | Step-1: Go to Site Step-2: Go to All the Pages |  |  | Passed
111 |  |  |  | Verifying user can search for product using the searchbar | User should be able to search for product using the searchbar | Found as per expected | napa | Step-1: Go to Site Step-2: Search for product |  |  | Passed
112 |  |  |  | Verifying search results automatically appear while typing search query | Search results should automatically appear as the search query is being made | Found as per expected | Na | Step-1: Go to Site Step-2: Search for product |  |  | Passed
113 |  |  |  | Verifying user can search exact product | User should be able to search for exact product | Found as per expected | Napa 500mg suppository | Step-1:Go to Site Step-2: Search for product |  |  | Passed
114 |  |  |  | Verifying search result aren't case sensitive | Search results shouldn't be case sensitive. User can search with upper/lower case | Found as per expected | NAPA | Step-1:Go to Site Step-2: Search for product |  |  | Passed
115 |  |  |  | Verifying search result for unavailable product | A message should be displayed about no product being available | Found as per expected | enfamil | Step-1:Go to Site Step-2: Search for product |  |  | Passed
116 |  |  |  | Verifying search result with search query of special character | No product should be displayed and a message should be displayed about product not being available | Found as per expected | # | Step-1:Go to Site Step-2: Search for product |  |  | Passed
117 |  |  |  | Verifying when a search product is shown it has its image,name, price and add to bag button | Each search result product should have an image, name, price and add to bag button | Found as per expected | Napa | Step-1:Go to Site Step-2: Search for product |  |  | Passed
118 |  |  |  | Verifying add to bag button on search result product is working | The add to bag button on each search result product should be working and product should be added to cart if add to button is clicked | Found as per expected |  | Step-1:Go to Site Step-2: Search for product Step-3: Click on Add to Bag Button of search result |  |  | Passed
119 |  |  |  | Verifying quantity can be updated for added to cart product | User should be able to update product quantity after clicking on add to bag button | Found as per expected |  | Step-1:Go to Site Step-2: Search for product Step-3: Click on Add to Bag Button of search result Step-4: Click on +/- button to update the quantity |  |  | Passed
120 |  |  |  | Verifying view all button under search result is working | View All button should take the user to a page that shows all the product that matches the search query | Found as per expected |  | Step-1:Go to Site Step-2: Search for product Step-3: Click on View All |  |  | Passed
121 |  |  |  | Verifying all product cards are displayed accordingly in the view all search result page | All product cards should be displayed accordingly in the view all search result page | Found as per expected |  | Step-1:Go to Site Step-2: Search for product Step-3: Click on View All |  |  | Passed
122 |  |  | Product Card | Verifying each product card has image, product name, product category, price and add to bag button | Each product card should have image, product name, product category, price and add to bag button | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category |  |  | Passed
123 |  |  |  | Verifying hovering on product image zooms in the product image | Hovering on product image should zoom in the image | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Hover on product image |  |  | Passed
124 |  |  |  | Verifying Add to Bag button works | Clicking on Add to Bag button should add the product to cart | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on Add to Bag button |  |  | Passed
125 |  |  |  | Verifying product quantity can be updated from details page | Clicking on add to bag button should open up quantity amount and there should be option increase or decrease quantity | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on Add to Bag button Step-4: Click on +/- to increase/decrease quantity |  |  | Passed
126 |  |  |  | Verifying clicking on any product card loads the product details page of the clicked product | Clicking on any product card should load the product details page of the clicked product | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on the product card |  |  | Passed
127 |  |  |  | Verifying product details page has product image, name, generic name,supplier name, price and add to bag button | Product details page should have product image, name, generic name,supplier name, price and add to bag button | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on the product card |  |  | Passed
128 |  |  |  | Verifying information tab of the product details page has information of the product | Information tab of the product details page has information of the product | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on the product card Step-4: Click on Information tab |  |  | Passed
129 |  |  |  | Verifying review tab has a input field to write review about the product | There should be an input field to write review about the product | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on the product card Step-4: Click on Review tab |  |  | Passed
130 |  |  |  | Verifying related product section beside the details of the product | There should be a related product section right beside the product details | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on the product card |  |  | Passed
131 |  |  | Product Cart | Verifying number of product in cart and total price updates with product being added or removed | The total number of product in cart should be displayed along with total price. The number of product and price should update if product is added/removed from cart | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on add to bag button |  |  | Passed
132 |  |  |  | Verifying all added products are showing on cart | All added product should have their name, unit price and number of unit wanted total price for each product and a remove button to remove the product | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on add to bag button |  |  | Passed
133 |  |  |  | Verifying product quantity can be updated from product cart | Clicking on +/- icon on the cart of any product should update the quantity wanted of that product | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on add to bag button Step-4: Open cart Step-5: Click on +/- to update quantity |  |  | Passed
134 |  |  |  | Verifying updating quantity changes product sub total price and the total price automatically with quantity being incresed or decreased | Updating quantity should change product sub total price and the total price automatically with quantity being incresed or decreased | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on add to bag button Step-4: Open cart Step-5: Click on +/- to update quantity |  |  | Passed
135 |  |  |  | Verifying remove button on each product of the cart is working | Clicking on remove button of each product should remove that product from the cart | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on add to bag button Step-4: Open cart Step-5: Click on remove button |  |  | Passed
136 |  |  |  | Verifying clicking on clear all button removes all the product from the cart | Clicking on clear all button should remove all the product from the cart | Found as per expected |  | Step-1:Go to Site Step-2: Click on any category Step-3: Click on add to bag button Step-4: Open cart Step-5: Click on clear all button |  |  | Passed
137 |  |  |  | Verifying order now button activity if clicked with no product on cart | If there is no product on cart, clicking on Order Now button shouldn't take the user to checkout page, rather it should show an error message | Found as per expected with error message "There is no product in the shopping bag" |  | Step-1:Go to Site Step-2: Open cart Step-3: Click on Order Now |  |  | Passed
138 |  |  |  | Verifying clicking on order now button takes the user to checkout page if some product/s are added to the cart | Clicking on order now button while product/s are there on cart should take the user to checkout page | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now |  |  | Passed
139 |  |  | Checkout | Verifying product list is displayed on checkout page | The list of added product should be displayed on checkout page | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now |  |  | Passed
140 |  |  |  | Verifying product list table has the specified columns | Product list table should have product image, product name, product description, price, quantity, amount and action | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now |  |  | Passed
141 |  |  |  | Verifying product quantity can be updated from the product list in checkout page | User should be able to update product quantity from the product list in checkout page | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Click on +/- icon on the Qty column |  |  | Passed
142 |  |  |  | Verifying Amount is updated as the quantity changes | The amount should update if the product quantity changes | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Click on +/- icon on the Qty column |  |  | Passed
143 |  |  |  | Verifying if quantity is decreased to 0, the product is removed from the list in checkout page | If quantity is decreased to 0, the product should be removed from the list in checkout page | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Decrease the quantity to 0 |  |  | Passed
144 |  |  |  | Verifying clicking on remove action of each product in product list | Clicking on remove icon should remove the product from the list | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Click on remove icon |  |  | Passed
145 |  |  |  | Verifying user is taken away from the checkout page if the user removes all the product from product list | User should be taken away from the checkout page if the user removes all the product from product list | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Remove all the product from the list |  |  | Passed
146 |  |  |  | Verifying coupon code input field is displayed under the product list table | User should see a Coupon Code input field under the product table | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now |  |  | Passed
147 |  |  |  | Verifying invalid coupon is caught during processing | Invalid coupon should be caught after applying the coupon and user should be shown an error message | Found as per expected | LAZZPHARMA | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5:Input Coupon code and apply |  |  | Passed
148 |  |  |  | Verifying valid couple is successfully applied | Valid coupon should be successfully applied and cost reduction should be showed due to coupon in the pricing section | [5 empty] | Out of Scope
149 |  |  |  | Verifying Amount is displayed accurately in the pricing section | The total amount of price should be displayed accurately in the pricing section | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now |  |  | Passed
150 |  |  |  | Verifying Delivery charge is showing according to the Inside/Outside Dhaka City policy | The delivery charge inside dhaka city should be 80 Taka and Outside dhaka city should be 120 Taka | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Add Region and City |  |  | Passed
151 |  |  |  | Verifying Total Amount is accurately displayed | The summation of amount and delivery charge should be properly displayed as Total Amount | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Add Region and City |  |  | Passed
152 |  |  |  | Verifying Receiver's name and phone number is fetched from the account info and shown in receiver's info section, if user logged in | If the user is logged in, receiver's name and phone number should be fetched from the account info and shown in receiver's info section | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now |  |  | Passed
153 |  |  |  | Verifying user can not place order without filling out all the required fields in the page | User should fill out all the required page to send product request | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Click on place order |  |  | Passed
154 |  |  |  | Verifying user can select region from dropdown | User should be able to select region among the 7 division from the dropdown | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Click on Region |  |  | Passed
155 |  |  |  | Verifying City dropdown is updated according to the selected region | Whenever the user select a region the City dropdown should be updated with the cities of that region | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Select Region Step-6: Click on City |  |  | Passed
156 |  |  |  | Verifying Area dropdown is updated according to the selected city | Whenever the user select a city the area dropdown should be updated with the areas of that city | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Select Region Step-6: Select City Step-7: Click on Area |  |  | Passed
157 |  |  |  | Verifying pay first and order reconfirm calling policy is mentioned at the bottom | The information about the pay first policy for outside dhaka city order and LP agent calling for delivery charge and order charge reconfirmation for finalizing the order is mentioned clearly | Found as per expected |  | Step-1:Go to Site Step-2:Add product to bag Step-3: Open cart Step-4: Click on Order Now |  |  | Passed
158 |  |  |  | Verifying prescription can be uploaded in the checkout page | User should be able to upload prescription using the select prescription button and the image of the prescription should show up on the page | Found as per expected |  | Step-1:Go to Site Step-2: Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Click on Select Prescription |  |  | Passed
159 |  |  |  | Verifying user can proceed with cash on delivery option | User should be able to choose cash on delivery and pay when the delivery arrives | Found as per expected |  | Step-1:Go to Site Step-2: Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Fill out all the fields Step-6: Click on Cash on Delivery Step-7: Click on Place Order |  |  | Passed
160 |  |  |  | Verifying user can place order | User should be able to place order after providing all the information | Found as per expected |  | Step-1:Go to Site Step-2: Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Fill out all the fields Step-7: Click on Place Order |  |  | Passed
161 |  |  |  | Verifying user can place auto order after 28 days | User should be able to place auto order after providing all the information | Found as per expected |  | Step-1:Go to Site Step-2: Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Fill out all the fields Step-7: Click on Auto Order |  |  | Passed
162 |  |  |  | Verifying user is given an order ID and success message after successfull order | User should be given an order ID and success message after successfull order | Found as per expected |  | Step-1:Go to Site Step-2: Add product to bag Step-3: Open cart Step-4: Click on Order Now Step-5: Fill out all the fields Step-7: Click on Auto Order |  |  | Passed
163 | Request Order |  | Request Order | Verifying user can access the request order page | Users should be able to access the request order page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order |  |  | Passed
164 |  |  |  | Verifying all the fields are required to add product to request order | All the fields (eg: Product Name, Strength, Quantity) should be required to add product | Found as per expected | Napa Extra,0 | Step-1: Go to Site Step-2: Click on Request Order Step-3: Try to add product with one/more fields empty |  |  | Passed
165 |  |  |  | Verifying clicking add button while keeping empty fields shows an error message | User should be shown an error message if some fields are empty | Found as per expected with error message "Name, Strenth and Quantity Required!" |  | Step-1: Go to Site Step-2: Click on Request Order Step-3: Try to add product with one/more fields empty |  |  | Passed
166 |  |  |  | Verifying products can be added by filling out all the required fields | Products should be added for requesting order by filling out all the fields | Found as per expected | Napa Extra, 5 Mg, 1 | Step-1: Go to Site Step-2: Click on Request Order Step-3: Fill out the necessary fields to add product |  |  | Passed
167 |  |  |  | Verifying whether product can be added if the quantity is 0 or less than 0 | Product should not be added if the quantity is less than or equal 0 | Not found as per expected. Negative/Zero quantity product can be added | Napa Extra, 5 Mg, -2, Esoral, 20 MG, 0 | Step-1: Go to Site Step-2: Click on Request Order Step-3: Fill out the necessary fields to add product | zero_&_negative_quantity_added_error.png |  | Failed
168 |  |  |  | Verifying added product can be removed by clicking on remove button | Remove button should remove the selected product | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order Step-3: Fill out the necessary fields to add product Step-4: Click on Remove Button |  |  | Passed
169 |  |  |  | Verifying prescription can be uploaded using the select prescription button | User should be able to upload prescription by clicking on select prescription button | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order Step-3: Click on Select Prescription |  |  | Passed
170 |  |  |  | Verifying delivery charge is displayed on the top as note | Delivery charge inside and outside Dhaka should be displayed on top as note for user conveinience | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order |  |  | Passed
171 |  |  |  | Verifying User's name and phone number is automatically filled if the user is logged in | User's name and Phone number field should be automatically filled if the user is logged in | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order |  |  | Passed
172 |  |  |  | Verifying user can not send product required without filling out all the required fields in the page | User should fill out all the required page to send product request | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order Step-3: Click on Send Product Request with some fields empty |  |  | Passed
173 |  |  |  | Verifying user can select region from dropdown | User should be able to select region among the 7 division from the dropdown | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order Step-3: Click on Region |  |  | Passed
174 |  |  |  | Verifying City dropdown is updated according to the selected region | Whenever the user select a region the City dropdown should be updated with the cities of that region | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order Step-3: Select a Region Step-4: Click on City |  |  | Passed
175 |  |  |  | Verifying Area dropdown is updated according to the selected city | Whenever the user select a city the area dropdown should be updated with the areas of that city | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order Step-3: Select a Region Step-4: Select a City Step-5: Click on Area |  |  | Passed
176 |  |  |  | Verifying user must check the terms and Condition accept box to process with the request | User should check the terms and condition box to proceed with the request | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order Step-3: Fill all the fields Step-4: Click on Send Product Request without checking the terms and condition box |  |  | Passed
177 |  |  |  | Verifying user is shown an error message if the terms and Condition box is unchecked | User should be shown an error message if the terms and Condition box is unchecked | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order Step-3: Fill all the fields Step-4: Click on Send Product Request without checking the terms and condition box |  |  | Passed
178 |  |  |  | Verifying user is shown a success message if the order is placed | User should be shown a success message if the order is placed | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order Step-3: Fill all the fields Step-4: Click on Send Product Request with checking the terms and condition box |  |  | Passed
179 |  |  |  | Verifying user can view order by clicking on view order button after completing order request | User should be able to view the order by clicking on view order button | Found as per expected |  | Step-1: Go to Site Step-2: Click on Request Order Step-3: Fill all the fields Step-4: Click on Send Product Request with checking the terms and condition box Step-5: Click on View Order |  |  | Passed
180 | Special Offers |  | Special Offer | Verifying user can access the special offers page | User should be able to access the special offers page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Special Offers |  |  | Passed
181 |  |  |  | Verifying if no special offer is available the message is shown | If there isn't any special offers available, a message should be shown regarding that | Found as per expected |  | Step-1: Go to Site Step-2: Click on Special Offers |  |  | Passed
182 |  |  |  | Verifying special offers are shown, if available | All the available special offers should be shown in this page |  |  | Step-1: Go to Site Step-2: Click on Special Offers |  |  | Out of Scope
183 |  |  |  | Verifying clicking on any special offers takes the user to a page containing details of that offer | Clicking on any special offers should take the user to a page containing details of that offer |  |  | Step-1: Go to Site Step-2: Click on Special Offers Step-3: Click on any special Offers |  |  | Out of Scope
184 |  |  |  | Verifying no grammartical or spelling mistake is present on the page | There shouldn't be any grammartical or spelling mistake | Not found as per expected. Mistake in the spelling of "available" |  | Step-1: Go to Site Step-2: Click on Special Offers | special_offers_pagespelling_error.png |  | Failed
185 | Branch Location |  |  | Verifying user can access the branch location page | User should be able to access the branch location page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Branch Locations |  |  | Passed
186 |  |  | Search Branch | Verifying user can see/access the search bar | User should be able to access the branch search bar to search branch | Found as per expected |  | Step-1: Go to Site Step-2: Click on Branch Locations |  |  | Passed
187 |  |  |  | Verifying user cam search branch by branch name | User should be able to search branch by branch name | Found as per expected | Sylhet,Demra | Step-1: Go to Site Step-2: Click on Branch Locations Step-3: Search Branch by branch name |  |  | Passed
188 |  |  |  | Verifying user can search branch by contact number | User should be able to search branch by contact number | Found as per expected | 1853090303 | Step-1: Go to Site Step-2: Click on Branch Locations Step-3: Search Branch by contact number |  |  | Passed
189 |  |  |  | Verifying user can search branch by location | User should be able to search branch by location | Found as per expected | Shahida Plaza | Step-1: Go to Site Step-2: Click on Branch Locations Step-3: Search Branch by location |  |  | Passed
190 |  |  |  | Verifying all search results are displayed below the search bar | User should be able to see the searched branch below the search bar | Found as per expected |  | Step-1: Go to Site Step-2: Click on Branch Locations Step-3: Search Branch |  |  | Passed
191 |  |  |  | Verifying page numbers below the search results works accordingly | The page numbers should take the user to the specifiied page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Branch Locations Step-3: Search Branch Step-4: Click on Page Number |  |  | Passed
192 |  |  |  | Verifying page NUMBERS updates with search being made | The page numbers should update while the search is made | Found as per expected |  | Step-1: Go to Site Step-2: Click on Branch Locations Step-3: Search Branch |  |  | Passed
193 |  |  | Map Location | Verifying clicking on any branch from the list displays the branch map location | Clicking on any branch from the branch list would display the branch map location below the list | Not found as per expected. The branch location is not loading on the map |  | Step-1: Go to Site Step-2: Click on Branch Locations Step-3: Search Branch Step-4: Click on a branch from the list | map_integration_error.png |  | Failed
194 | Company Info |  | Review | Verifying user can access the review page | User should be able to access the review page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Review |  |  | Passed
195 |  |  |  | Verifying user can see the reviews on the page | User should be able to see the reviews other posted on the page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Review |  |  | Passed
196 |  |  |  | Verifying the reviews has user name, review decription and posted time | Each review should have username, description and posted time | Found as per expected |  | Step-1: Go to Site Step-2: Click on Review |  |  | Passed
197 |  |  |  | Verifying pagination is working | Clicking on page number or next/previoius page should load the specific review page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Review Step-3: Click on Pagination |  |  | Passed
198 |  |  |  | Verifying whether review can be posted without filling out the review field | User should not be able to post empty review and should see an error message | Found as per expected |  | Step-1: Go to Site Step-2: Click on Review Step-3: Post an Empty review |  |  | Passed
199 |  |  |  | Verifying logged in user can post reviews and their username is shown along with the review | Users should be able to post reviews and their username should be shown on top of the review | Found as per expected |  | Step-1: Go to Site Step-2: Click on Review Step-3: Post a review |  |  | Passed
200 |  |  |  | Verifying whether logged out user can post a review | Logged out user should not be able to post review. if they try to, they should be redirected to the login modal | Found as per expected |  | Step-1: Go to Site Step-2: Click on Review Step-3: Post a review |  |  | Passed
201 |  |  | Gallery | Verifying user can access the gallery page | User should be able to access the gallery page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Gallery |  |  | Passed
202 |  |  |  | Verifying user can view the images on gallery | User should be able to view the images on gallery | Found as per expected |  | Step-1: Go to Site Step-2: Click on Gallery |  |  | Passed
203 |  |  |  | Verifying user can access the about us page | User should be able to access the about us page | Found as per expected |  | Step-1: Go to Site Step-2: Click on About Us |  |  | Passed
204 |  |  | Banner | Verifying there is a banner on about us page | There should be a banner in about us page | Found as per expected |  | Step-1: Go to Site Step-2: Click on About Us |  |  | Passed
205 |  |  |  | Verifying the navigation button on the carousal works | User should be able to navigate the carousal using the navigation button | Found as per expected |  | Step-1: Go to Site Step-2: Click on About Us Step-3: Navigate the carousal |  |  | Passed
206 |  |  |  | Verifying the banner contains information on "Who Are We" | The banner should contain information on "Who Are We" about Lazz Pharma | Found as per expected |  | Step-1: Go to Site Step-2: Click on About Us |  |  | Passed
207 |  |  | Board of Director | Verifying the about us page has information on board of director | The About Us page should have information on Board of Director | Found as per expected |  | Step-1: Go to Site Step-2: Click on About Us |  |  | Passed
208 |  |  |  | Verifying the Name and Designation of the board of director are shown with their photo | The photo, name and Designation of the board of Director members should be displayed | Found as per expected |  | Step-1: Go to Site Step-2: Click on About Us |  |  | Passed
209 |  |  | Corporate Associate | Verifying the Corporate Associate members information is shown in About Us Page | The About Us page should have information on Corporate Associate members | Found as per expected |  | Step-1: Go to Site Step-2: Click on About Us |  |  | Passed
210 |  |  |  | Verifying each Corporate Associate Member should have their name, designation on their image | Each Corporate Associate Member should have their name, designation on their image | Found as per expected |  | Step-1: Go to Site Step-2: Click on About Us |  |  | Passed
211 |  |  |  | Verifying user can access the contact us page | User should be able to access the Contact Us page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Contact Us |  |  | Passed
212 |  |  | Contact Form | Verifying contact form is displayed on contact us page | Contact form should be displayed on contact us page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Contact Us |  |  | Passed
213 |  |  |  | Verifying Contact form has Message, Name, Phone and Email field | Contact should have Message, Name, Phone and Email field | Found as per expected |  | Step-1: Go to Site Step-2: Click on Contact Us |  |  | Passed
214 |  |  |  | Verifying Message, Name and Phone Number field is required to send message to Lazz pharma | Message, Name and Phone Number field should be required to send message to Lazz pharma | Found as per expected | Test Message | Step-1: Go to Site Step-2: Click on Contact Us Step-3: Send Message without filling some fields |  |  | Passed
215 |  |  |  | Verifying user can send message to lazz pharma using the contact form | User should be able to send message to lazz pharma using the contact form | Found as per expected | Test Message, Kawsar, 01732066805 | Step-1: Go to Site Step-2: Click on Contact Us Step-3: Send Message with filling the fields |  |  | Passed
216 |  |  |  | Verifying user is shown a success message after they sent a message | User should be shown a success message after they sent a message | Found as per expected with a success message "Sent message successfully." |  | Step-1: Go to Site Step-2: Click on Contact Us Step-3: Send Message with filling the fields |  |  | Passed
217 |  |  | Contact Info | Verifying lazz pharma's phone number is displayed on the contact page | Lazz pharma's phone number should be displayed on the contact page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Contact Us |  |  | Passed
218 |  |  |  | Verifying lazz pharma's email is displayed on the contact page | Lazz pharma's Email should be displayed on the contact page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Contact Us |  |  | Passed
219 |  |  | Franchise Info | Verifying user can access the franchise info page | User should be able to access the franchise info page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Franchise Info |  |  | Passed
220 |  |  |  | Verifying franchise info is shown in franchise info page | Franchise Information should be displayed on Franchise info page | Found as per expected |  | Step-1: Go to Site Step-2: Click on Franchise Info |  |  | Passed
221 |  |  |  | Verifying franchise information can be downloaded | Franchise information can be downloaded using the download button | Found as per expected |  | Step-1: Go to Site Step-2: Click on Franchise Info |  |  | Passed
222 | Footer |  |  | Verifying user can see the lazz pharma logo, address, mobile and email of lazz pharma in footer | User should be able to view the lazzpharma logo, their address, mobile and email in the left corner of the footer | Found as per expected |  | Step-1:Go to Site Step-2: Go to footer |  |  | Passed
223 |  |  |  | Verifying spelling mistakes in footer | There shouldn't be any spelling mistakes in footer | Not found as per expected. "Career" is wrongly spelled as "Carrer" |  | Step-1:Go to Site Step-2: Go to footer | footer_career_spelling_error.png |  | Failed
224 |  |  | For Customer | Verifying user are redirected to order request page after clicking on Request Order in footer | User should be redirected to order request page after clicking on Request Order in footer | Found as per expected |  | Step-1:Go to Site Step-2: Click on Request Order in Footer |  |  | Passed
225 |  |  |  | Verifying user are redirected to prescription selection page after clicking on Upload Prescription in footer | User should be redirected to prescription selection page after clicking on Upload Prescription in footer | Not found as per expected. User are taken to the top of the home page |  | Step-1:Go to Site Step-2: Click on Upload Prescription in Footer | footer_upload_prescription_error.mp4 |  | Failed
226 |  |  |  | Verifying user are redirected to review page after clicking on Site Review in footer | User should be redirected to review page after clicking on Site Review in footer | Found as per expected |  | Step-1:Go to Site Step-2: Click on Site Review in Footer |  |  | Passed
227 |  |  |  | Verifying user are redirected to special offers page after clicking on Special Offers in footer | User should be redirected to special offers page after clicking on Special Offers in footer | Found as per expected |  | Step-1:Go to Site Step-2: Click on Special Offers in Footer |  |  | Passed
228 |  |  |  | Verifying user are redirected to how to order page after clicking on How To Order in footer | User should be redirected to How to order page after clicking on How To Order in footer | Found as per expected |  | Step-1:Go to Site Step-2: Click on How To Order in Footer |  |  | Passed
229 |  |  |  | Verifying how to order page has specific set of instruction and a youtube tutorial on how to order | How to order page should have specific set of instruction and a youtube tutorial on how to order | Found as per expected |  | Step-1:Go to Site Step-2: Click on How To Order in Footer |  |  | Passed
230 |  |  | Support | Verifying user are redirected to career page after clicking on Career in footer | User should be redirected to career page after clicking on Career in footer | Found as per expected |  | Step-1:Go to Site Step-2: Click on Career in Footer |  |  | Passed
231 |  |  |  | Verifying current job opportunities are displayed in career page | Current job opportunities should be displayed in career page, if available | Found as per expected |  | Step-1:Go to Site Step-2: Click on Career in Footer |  |  | Passed
232 |  |  |  | Verifying user are redirected to contact us page after clicking on Contact Us in footer | User should be redirected to contact us page after clicking on Contact Us in footer | Found as per expected |  | Step-1:Go to Site Step-2: Click on Contact us in Footer |  |  | Passed
233 |  |  |  | Verifying user are redirected to Return Policy page after clicking on Return Policy in footer | User should be redirected to Return Policy page after clicking on Return Policy in footer | Found as per expected |  | Step-1:Go to Site Step-2: Click on Return Policy in Footer |  |  | Passed
234 |  |  |  | Verifying return policy are clearly stated in return policy page | Return policy should be clearly stated in return policy page | Found as per expected |  | Step-1:Go to Site Step-2: Click on Return Policy in Footer |  |  | Passed
235 |  |  |  | Verifying user are redirected to Terms and Condition page after clicking on Terms and Condition in footer | User should be redirected to Terms and Condition page after clicking on Terms and Condition in footer | Found as per expected |  | Step-1:Go to Site Step-2: Click on Terms and Conditions in Footer |  |  | Passed
236 |  |  |  | Verifying Terms and Condition are clearly stated in Terms and Condition page | Terms and Condition should be clearly stated in Terms and Condition page | Found as per expected |  | Step-1:Go to Site Step-2: Click on Terms and Conditions in Footer |  |  | Passed
237 |  |  |  | Verifying user are redirected to Privacy Policy page after clicking on Privacy Policy in footer | User should be redirected to Privacy Policy page after clicking on Privacy Policy in footer | Found as per expected |  | Step-1:Go to Site Step-2: Click on Privacy Policy in Footer |  |  | Passed
238 |  |  |  | Verifying Privacy Policy are clearly stated in Privacy Policy page | Privacy Policy should be clearly stated in Privacy Policy page | Found as per expected |  | Step-1:Go to Site Step-2: Click on Privacy Policy in Footer |  |  | Passed
239 |  |  |  | Verifying all social icons in the footer are redirecting user to the corresponding social site | All social icons in the footer should be redirecting user to the corresponding social site, if clicked | Not found as per expected. all the social icons are taking the user to the facebook page of lazzpharma |  | Step-1:Go to Site Step-2: Click on Social Media icons in Footer | social_media_link_error.mp4 |  | Failed
240 | General |  | Browser Compatibility | Verifying various browser compatibility | Should run in different browsers | Found as per expectation | Chrome,Edge,Firefox | Step-1:Open Browser Step-2: Search using the site URL |  |  | Passed
241 |  |  |  | Verifying website responsiveness | Website should be responsive accross various devices | Found as per expectation |  | Step-1:Open Browser Step-2: Search using the site URL |  |  | Passed
Negative test

## Bug Report
Bug Reporting
#SL 01
Issue: User is taken to OTP verification modal even after entering an invalid mobile number during sign-up.
Reproducing Steps:
1. Go to the URL: https://www.lazzpharma.com/
2. Click on the Login button
3. Click on Sign Up
4. Enter an Invalid Phone Number and password to SignUp
Env: Production
Module: Sign Up
Priority: P1
Severity: Major
ScreenShot: Invalid_phone_number_error.png
Expectation: The system should validate the mobile number before proceeding. If the number is invalid,
display a clear error message like: "Please enter a valid mobile number." and prevent the transition to the OTP
verification step.
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 02
Issue: After uploading a prescription and adding a note, clicking the "Save & Order" button results in no action.
The order process does not proceed as expected.
Reproducing Steps:
1. Go to the URL: https://www.lazzpharma.com/
2. Login to the site
3. Go to Prescription History
4. Upload a prescription image.
5. Add a note
6. Click on "Save & Order"
Env: Production
Module: Prescription History
Priority: P1
Severity: Major
ScreenShot: prescription_order_error.png
Expectation: Once a valid prescription is uploaded and a note is provided, clicking "Save & Order" should
save the prescription, place the order and provide visual information
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 03
Issue: Clicking the "View All" button under each Featured Product Category on the home page does not
redirect to the corresponding category-wise product listing page.
Reproducing Steps:
1. Go to the URL: https://www.lazzpharma.com/
2. Scroll down to the Featured Product Categories section.
3. Click on the "View All" button for any category (e.g., Baby Care, Health Care, etc.).
Env: Production
Module: Home
Priority: P2
Severity: Major
ScreenShot: view_all_button_error.mp4
Expectation: Each "View All" button should correctly redirect to a category-specific product listing page showing
all products under the selected category.
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 04
Issue: When a user navigates to a product category page with no available products, the page remains blank
instead of showing a meaningful message.
Reproducing Steps:
1. Go to the URL: https://www.lazzpharma.com/
2. Hover over or click the “CATEGORIES” dropdown from the top navigation bar.
3. Select any category that currently has no products (e.g., “Health Condition”).
Env: Production
Module: Product Management
Priority: P3
Severity: Minor
ScreenShot: product_unavailable_message_error.png
Expectation: If there are no products under a selected category, the system should display a user-friendly
message, such as:
"No products found under this category. Please check back later."
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 05
Issue: Users are allowed to add products with quantity 0 or less on request order page, which should not be
possible.
Reproducing Steps:
1. Go to the URL: https://www.lazzpharma.com/
2. Navigate to the “Request Order” page from the top navigation bar.
3. Fill product name, strength and set the quantity to 0 or a negative number (e.g., -1).
4. Click on Add button
Env: Production
Module: Request Order
Priority: P2
Severity: Major
ScreenShot: zero_&_negative_quantity_added_error.png
Expectation: The system should validate the quantity before adding the product. It should prevent the item from
being added and show an error or warning like:
"Please enter a valid quantity greater than 0."
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 06
Issue: The word "Avaiable" is used instead of "Available" in special offers page.
possible.
Reproducing Steps:
1. Go to the URL: https://www.lazzpharma.com/
2. Navigate to the “Special Offers” page from the top navigation bar.
Env: Production
Module: Special Offers
Priority: P4
Severity: Minor
ScreenShot: special_offers_pagespelling_error.png
Expectation: The text should be: "No Offer Currently Available"
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 07
Issue: Google Map not loading correctly on the Branch Locations page
Reproducing Steps:
1. Go to the URL: https://www.lazzpharma.com/
2. Click on Branch Locations from the navigation menu.
3. In the displayed list, click on any branch name.
Env: Production
Module: Branch Location
Priority: P3
Severity: Minor
ScreenShot: map_integration_error.png
Expectation: When a branch is clicked, a fully interactive Google Map with the correct branch location pin
should load.
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 08
Issue: Spelling mistake in Refill Order modal – "Cancel" is wrongly typed as "Cancle"
Reproducing Steps:
1. Go to the URL: https://www.lazzpharma.com/
2. Navigate to the Order List section.
3. Click on Refil of any previous order.
Env: Production
Module: Order History
Priority: P4
Severity: Minor
ScreenShot: refil_modal_spelling_error.png
Expectation: The button should be correctly labeled as "Cancel".
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 09
Issue: "Upload Prescription" link in the footer redirects to the top of the homepage instead of the upload section
Reproducing Steps:
1. Go to the URL: https://www.lazzpharma.com/
2. Scroll to the bottom of the page and click on the "Upload Prescription" link in the footer.
Env: Production
Module: Footer
Priority: P3
Severity: Minor
ScreenShot: footer_upload_prescription_error.mp4
Expectation: Clicking "Upload Prescription" should take the user to the appropriate section or a separate upload
prescription page, not just scroll to the top.
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 10
Issue: Spelling mistake in the footer – "Career" is incorrectly typed as "Carrer"
Reproducing Steps:
1. Go to the URL: https://www.lazzpharma.com/
2. Scroll to the footer
Env: Production
Module: Footer
Priority: P4
Severity: Minor
ScreenShot: footer_career_spelling_error.png
Expectation: The text should be correctly spelled as "Career".
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 11
Issue: All social media icons in the footer redirect to the Facebook page of LazzPharma
Reproducing Steps:
1. Go to the URL: https://www.lazzpharma.com/
2. Scroll to the footer
3. Click on each social media icon
Env: Production
Module: Footer
Priority: P4
Severity: Minor
ScreenShot: social_media_link_error.mp4
Expectation: Each social icon should redirect to its corresponding platform/page
Responsible QA: Md. Kawsar Hossain

## Test Summary Report
Test Case Report | [5 empty] | Result :
Project Name | Lazz Pharma Limited
Module Name | Account, Home, Product Management Request Order, Special Request, Branch Location, Company Info, Footer
Feature Name | Sign Up, Login, Logout, Profile, Order History, Prescription History, Request History, Submit Complain, Payment History, Banners, Marquee, Service Highlights, Featured Products, Resort Banner,Categories, Product Search, Product Card, Product Cart, Checkout, Request Order, Special Offers, Search Branch, Branch List, Map Location, Company info, Footer |  |  |  |  | Total No. | Status
Test Case Version | 1 |  |  |  |  | 227 | PASS
Written By | Md. Kawsar Hossain |  |  |  |  | 11 | FAIL
Executed By | Md. Kawsar Hossain |  |  |  |  | 0 | Not Executed
Reviewed By | [5 empty] | 3 | Out of Scope
TEST EXECUTION REPORT
Testing Environment : Google Chrome Browser
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 227 | 11 | 0 | 3 | 241
Grand Total | 227 | 11 | 0 | 3 | 241
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (238/238)*100 = 100%
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/238)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (227/238)*100 = 95.4%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (11/238)*100 = 4.6%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/241)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A